## Cover
MediBridge
Clinical Operations Platform - Product Backlog
Architecture is delivered in two independent parts (not wired together):
Frontend | HTML + CSS + vanilla JavaScript. Standalone prototype using browser localStorage. Presented on its own.
Backend | Vanilla Java + JDBC + PostgreSQL. TERMINAL / console application. Presented on its own.
Integration | Out of scope - no API layer; frontend and backend/DB are demoed separately.
Sheets | User Stories ¦ Subtasks ¦ Epics ¦ Scope & Assumptions ¦ Backend DB Schema
Legend | Priority = MoSCoW (Must/Should/Could). Points = Fibonacci. Status: Frontend = Done, Backend = To Do.
Totals | 22 user stories ¦ 97 subtasks ¦ 10 epics ¦ 168 story points

## User Stories
ID | Epic | Layer | Role | User Story | Acceptance Criteria (key) | Priority | Points | # Subtasks | Status | Wireframe(s)
US-01 | E1 Authentication & Access | Frontend | All | Authentication & login | Role selection updates imagery; valid creds route to role home; invalid show inline error; admin via dedicated portal. | Must | 8 | 5 | Done | US-01-login-register.html
US-02 | E1 Authentication & Access | Frontend | Doctor/Patient/Staff | Registration & security questions | Step 1 collects name/email/password (+clinic code for staff); step 2 sets 3 hashed questions; admin cannot self-register. | Must | 8 | 6 | Done | US-02-register-security-questions.html, US-01-login-register.html
US-03 | E1 Authentication & Access | Frontend | All | Account recovery | Identify by email; verify 3 questions (case-insensitive); lock after 3 fails; reset password with strength meter. | Must | 5 | 5 | Done | US-03-forgot-password-verify.html, US-03-forgot-password-reset.html
US-04 | E2 Shared UI Platform | Frontend | All | Shared UI platform & account | Reusable store, modals, validation, toasts, breadcrumbs, design system, and the account & security page. | Must | 8 | 7 | Done | US-04-account.html
US-05 | E3 Institute Admin | Frontend | Admin | Admin dashboard & staff governance | KPIs, volume trend, clinics quick view, staff table; onboard and deboard staff via modals. | Must | 8 | 6 | Done | US-05-admin-dashboard.html
US-06 | E3 Institute Admin | Frontend | Admin | Clinic enrollment & directory | Directory lists all clinics; enroll modal captures name/specialty/address and generates a unique clinic code. | Must | 5 | 3 | Done | US-06-admin-clinics.html
US-07 | E4 Doctor Workspace | Frontend | Doctor | Doctor dashboard & document requests | Bento dashboard with roster, daily schedule, request tracker; privacy-preserving document request modal. | Must | 8 | 6 | Done | US-07-doctor-dashboard.html
US-08 | E4 Doctor Workspace | Frontend | Doctor | Doctor scheduling (weekly & monthly) | Weekly gantt shows slots/breaks/appointments; monthly grid with switcher; availability configurable. | Must | 8 | 4 | Done | US-08-doctor-schedule-weekly.html, US-08-doctor-schedule-monthly.html
US-09 | E4 Doctor Workspace | Frontend | Doctor | Doctor patient records & notes | Searchable directory; scoped clinical chart; consented shared docs only; log consultation notes; request docs. | Must | 8 | 5 | Done | US-09-doctor-patients.html, US-09-doctor-patient-chart.html
US-10 | E5 Receptionist | Frontend | Receptionist | Receptionist intake, triage & directory | Intake KPIs, pending queue, availability roster; assign slots via review modal; patient directory. | Must | 8 | 7 | Done | US-10-receptionist-dashboard.html, US-10-receptionist-patients.html
US-11 | E6 Patient Experience | Frontend | Patient | Patient Health Hub | Overview, consent panel, timeline; request appointment (doctor-exists guard) and grant document access. | Must | 8 | 6 | Done | US-11-patient-hub.html
US-12 | E6 Patient Experience | Frontend | Patient | Patient appointments | Calendar with appointment dots, upcoming and pending lists, and a request-appointment modal. | Should | 5 | 3 | Done | US-12-patient-appointments.html
US-13 | E6 Patient Experience | Frontend | Patient | Patient document vault & consent | Real-file upload (4MB cap), document list, grant-access modal, and PDF/image preview. | Must | 8 | 5 | Done | US-13-patient-vault.html
US-14 | E6 Patient Experience | Frontend | Patient/Public | Patient digital ID & QR sharing | ID pass with contact/medical info (validated phone); from-scratch QR encodes a public read-only share URL. | Should | 8 | 4 | Done | US-14-patient-profile.html, US-14-patient-share.html
US-15 | E7 Public & Docs | Frontend | Public/All | Public landing, PWA & wireframes | Landing page communicates value + roles; PWA assets present; low-fi wireframes for all pages & popups. | Should | 5 | 3 | Done | US-15-landing.html, index.html
US-16 | E8 Backend Database | DB | Backend | Database foundation (Postgres + JDBC) | Normalized schema created by idempotent DDL; JDBC connectivity works; default admin seeded. | Must | 13 | 4 | To Do
US-17 | E9 Backend Terminal Core | Backend | Backend | Terminal application core | Role-based console menus; salted SHA-256 login; RBAC; console recovery; robust input handling. | Must | 13 | 5 | To Do
US-18 | E10 Backend Domain & Audit | Backend | Backend/Admin | Admin backend operations | Console CRUD for clinics/staff with clinic-code generation and KPI aggregate queries. | Must | 8 | 3 | To Do
US-19 | E10 Backend Domain & Audit | Backend | Backend/Doctor | Doctor backend operations | Console read of schedule, upsert availability, insert document requests and consultation notes. | Must | 8 | 3 | To Do
US-20 | E10 Backend Domain & Audit | Backend | Backend/Receptionist | Receptionist backend operations | List pending requests; assign a slot creating an appointment and updating the request atomically. | Must | 5 | 2 | To Do
US-21 | E10 Backend Domain & Audit | Backend | Backend/Patient | Patient backend operations | Submit appointment request (doctor guard), upload document metadata, grant/revoke time-boxed consent. | Must | 8 | 3 | To Do
US-22 | E10 Backend Domain & Audit | Backend | Backend | Audit logging & reporting | Consent grant/revoke writes append-only audit rows; reporting queries print to console. | Should | 5 | 2 | To Do

## Subtasks
ID | User Story / Subtask | Layer | Priority | Est (h) | Status
US-01 | Authentication & login | Frontend | Must |  | Done
US-01-T1 | Split-screen layout + role selector (Doctor/Patient/Receptionist) with role-based imagery | Frontend |  | 3 | Done
US-01-T2 | Email/password sign-in with inline validation | Frontend |  | 2 | Done
US-01-T3 | Role-based redirect to correct home on success | Frontend |  | 2 | Done
US-01-T4 | Admin sign-in portal link + visual differentiation + default admin creds | Frontend |  | 3 | Done
US-01-T5 | Session persistence + requireAuth guard + logout | Frontend |  | 3 | Done
US-02 | Registration & security questions | Frontend | Must |  | Done
US-02-T1 | Step 1 form: full name, email, password with required markers | Frontend |  | 3 | Done
US-02-T2 | Clinic-code field + validation against enrolled clinics (doctor/staff) | Frontend |  | 2 | Done
US-02-T3 | Password strength meter & policy enforcement | Frontend |  | 2 | Done
US-02-T4 | Step 2: choose & answer 3 distinct security questions | Frontend |  | 2 | Done
US-02-T5 | SHA-256 salted hashing of answers (no plain-text) | Frontend |  | 2 | Done
US-02-T6 | Block admin self-registration | Frontend |  | 1 | Done
US-03 | Account recovery | Frontend | Must |  | Done
US-03-T1 | Identify account by registered email | Frontend |  | 1 | Done
US-03-T2 | Verify 3 security questions (case-insensitive hash match) | Frontend |  | 2 | Done
US-03-T3 | Lock flow after 3 failed attempts | Frontend |  | 1 | Done
US-03-T4 | Set new password with strength meter + confirm match | Frontend |  | 2 | Done
US-03-T5 | Sign-out-all-sessions toggle | Frontend |  | 1 | Done
US-04 | Shared UI platform & account | Frontend | Must |  | Done
US-04-T1 | localStorage data Store module (versioned CRUD) | Frontend |  | 3 | Done
US-04-T2 | Modal engine (overlay/Esc/close, scrollable responsive footers) | Frontend |  | 2 | Done
US-04-T3 | Form validation helpers (required *, phone, name, length, pattern, live-clear) | Frontend |  | 3 | Done
US-04-T4 | Toasts + insight popovers | Frontend |  | 2 | Done
US-04-T5 | Breadcrumb navigation on all pages | Frontend |  | 2 | Done
US-04-T6 | Design-system tokens & components; responsive desktop-first | Frontend |  | 3 | Done
US-04-T7 | Account & security page (profile info + change password) | Frontend |  | 2 | Done
US-05 | Admin dashboard & staff governance | Frontend | Must |  | Done
US-05-T1 | Command-center KPIs (clinics/facilities/staff/volume) + insight popovers | Frontend |  | 3 | Done
US-05-T2 | Patient volume trends chart | Frontend |  | 2 | Done
US-05-T3 | Enrolled clinics quick directory | Frontend |  | 2 | Done
US-05-T4 | Staff governance table with status (Active/On Leave/Inactive) | Frontend |  | 2 | Done
US-05-T5 | Onboard Staff modal (name, email, clinic, role) | Frontend |  | 3 | Done
US-05-T6 | Deboard Staff confirm modal (reassign consultations + revoke) | Frontend |  | 2 | Done
US-06 | Clinic enrollment & directory | Frontend | Must |  | Done
US-06-T1 | Clinics directory page (specialty, code, staff count, status) | Frontend |  | 2 | Done
US-06-T2 | Enroll New Clinic modal (name, specialty, address) + validation | Frontend |  | 3 | Done
US-06-T3 | Generate & display unique clinic code | Frontend |  | 2 | Done
US-07 | Doctor dashboard & document requests | Frontend | Must |  | Done
US-07-T1 | Bento dashboard KPIs | Frontend |  | 2 | Done
US-07-T2 | Today's patient roster with Open Record | Frontend |  | 2 | Done
US-07-T3 | Daily schedule gantt timeline | Frontend |  | 2 | Done
US-07-T4 | Request Clinical Document modal (no vault browsing) | Frontend |  | 3 | Done
US-07-T5 | Document request tracker + Shared-with-you list + preview | Frontend |  | 3 | Done
US-07-T6 | Set weekly availability modal | Frontend |  | 2 | Done
US-08 | Doctor scheduling (weekly & monthly) | Frontend | Must |  | Done
US-08-T1 | Weekly gantt: slots, breaks, appointment bars (visible w/o availability) | Frontend |  | 3 | Done
US-08-T2 | Next Up queue | Frontend |  | 2 | Done
US-08-T3 | Monthly calendar grid with month switcher | Frontend |  | 3 | Done
US-08-T4 | Set availability modal (working days, shift, lunch) | Frontend |  | 2 | Done
US-09 | Doctor patient records & notes | Frontend | Must |  | Done
US-09-T1 | Patient directory with search | Frontend |  | 2 | Done
US-09-T2 | Clinical chart: summary, history, allergies, upcoming (scoped) | Frontend |  | 3 | Done
US-09-T3 | Show only consented shared documents | Frontend |  | 2 | Done
US-09-T4 | Log consultation note | Frontend |  | 2 | Done
US-09-T5 | Request document modal from chart | Frontend |  | 2 | Done
US-10 | Receptionist intake, triage & directory | Frontend | Must |  | Done
US-10-T1 | Intake KPIs (scheduled/pending/on-duty) | Frontend |  | 2 | Done
US-10-T2 | Pending appointment requests queue | Frontend |  | 2 | Done
US-10-T3 | Doctor availability roster | Frontend |  | 2 | Done
US-10-T4 | Today's schedule list | Frontend |  | 1 | Done
US-10-T5 | Review & Schedule Request modal (assign doctor + slot, dispatch) | Frontend |  | 3 | Done
US-10-T6 | Doctor schedule inspection modal | Frontend |  | 2 | Done
US-10-T7 | Patient directory | Frontend |  | 2 | Done
US-11 | Patient Health Hub | Frontend | Must |  | Done
US-11-T1 | Overview + mini-stats + upcoming visit card | Frontend |  | 2 | Done
US-11-T2 | Consent & permissions panel (revoke) | Frontend |  | 2 | Done
US-11-T3 | Vault mini + my appointment requests list | Frontend |  | 2 | Done
US-11-T4 | Care & consultation timeline (gantt) | Frontend |  | 3 | Done
US-11-T5 | Request Appointment modal (doctor-exists guard) | Frontend |  | 3 | Done
US-11-T6 | Grant Document Access modal (files + duration) | Frontend |  | 3 | Done
US-12 | Patient appointments | Frontend | Should |  | Done
US-12-T1 | Month calendar with appointment dots + switcher | Frontend |  | 2 | Done
US-12-T2 | Upcoming & pending requests lists | Frontend |  | 2 | Done
US-12-T3 | Request Appointment modal | Frontend |  | 2 | Done
US-13 | Patient document vault & consent | Frontend | Must |  | Done
US-13-T1 | Drag & drop upload with real file storage (4MB cap) | Frontend |  | 3 | Done
US-13-T2 | My documents list (type/date, preview/share) | Frontend |  | 2 | Done
US-13-T3 | Pending requests + active access panels | Frontend |  | 2 | Done
US-13-T4 | Grant Document Access modal | Frontend |  | 2 | Done
US-13-T5 | Document preview (PDF/image, download fallback) | Frontend |  | 3 | Done
US-14 | Patient digital ID & QR sharing | Frontend | Should |  | Done
US-14-T1 | Digital ID pass page + contact/medical info (phone validation) | Frontend |  | 2 | Done
US-14-T2 | From-scratch QR code generator (SVG) | Frontend |  | 3 | Done
US-14-T3 | QR encodes shareable URL | Frontend |  | 2 | Done
US-14-T4 | Public read-only share pass page (no login) | Frontend |  | 2 | Done
US-15 | Public landing, PWA & wireframes | Frontend | Should |  | Done
US-15-T1 | Landing page (hero, roles, privacy band, footer) | Frontend |  | 3 | Done
US-15-T2 | PWA manifest & app icons | Frontend |  | 2 | Done
US-15-T3 | Wireframe documentation set (all pages + popups) | Frontend |  | 3 | Done
US-16 | Database foundation (Postgres + JDBC) | DB | Must |  | To Do
US-16-T1 | Design normalized Postgres schema (all entities) | DB |  | 5 | To Do
US-16-T2 | Write idempotent DDL (tables, enums, indexes) | DB |  | 5 | To Do
US-16-T3 | JDBC connection utility (config-driven) | DB |  | 3 | To Do
US-16-T4 | Seed default admin row (hashed) | DB |  | 2 | To Do
US-17 | Terminal application core | Backend | Must |  | To Do
US-17-T1 | Console menu framework (role-based menus, clean exit) | Backend |  | 5 | To Do
US-17-T2 | Console login with salted SHA-256 (parity with frontend) | Backend |  | 5 | To Do
US-17-T3 | RBAC enforcement per menu action | Backend |  | 3 | To Do
US-17-T4 | Console account recovery (3 questions, lockout) | Backend |  | 5 | To Do
US-17-T5 | Input validation & error handling | Backend |  | 3 | To Do
US-18 | Admin backend operations | Backend | Must |  | To Do
US-18-T1 | Enroll clinic & generate clinic code (insert) | Backend |  | 3 | To Do
US-18-T2 | Onboard / deboard staff (insert/update + reassign) | Backend |  | 5 | To Do
US-18-T3 | List clinics/staff & KPI aggregate queries | Backend |  | 3 | To Do
US-19 | Doctor backend operations | Backend | Must |  | To Do
US-19-T1 | View schedule & upsert availability | Backend |  | 5 | To Do
US-19-T2 | Request document (insert, no vault access) | Backend |  | 3 | To Do
US-19-T3 | Log consultation note (insert) | Backend |  | 2 | To Do
US-20 | Receptionist backend operations | Backend | Must |  | To Do
US-20-T1 | List pending requests (query) | Backend |  | 2 | To Do
US-20-T2 | Assign slot -> create appointment + update request (transaction) | Backend |  | 5 | To Do
US-21 | Patient backend operations | Backend | Must |  | To Do
US-21-T1 | Submit appointment request (guard: doctor exists) | Backend |  | 3 | To Do
US-21-T2 | Upload document metadata (insert) | Backend |  | 2 | To Do
US-21-T3 | Grant / revoke consent (time-boxed) | Backend |  | 5 | To Do
US-22 | Audit logging & reporting | Backend | Should |  | To Do
US-22-T1 | Append-only audit_log on consent grant/revoke etc. | Backend |  | 3 | To Do
US-22-T2 | Reporting queries printed to console (volume, roster) | Backend |  | 3 | To Do

## Epics
Epic | Layer | Stories | # Stories | Points
E1 Authentication & Access | Frontend | US-01, US-02, US-03 | 3 | 21
E2 Shared UI Platform | Frontend | US-04 | 1 | 8
E3 Institute Admin | Frontend | US-05, US-06 | 2 | 13
E4 Doctor Workspace | Frontend | US-07, US-08, US-09 | 3 | 24
E5 Receptionist | Frontend | US-10 | 1 | 8
E6 Patient Experience | Frontend | US-11, US-12, US-13, US-14 | 4 | 29
E7 Public & Docs | Frontend | US-15 | 1 | 5
E8 Backend Database | Backend/DB | US-16 | 1 | 13
E9 Backend Terminal Core | Backend/DB | US-17 | 1 | 13
E10 Backend Domain & Audit | Backend/DB | US-18, US-19, US-20, US-21, US-22 | 5 | 34

## Scope & Assumptions
Topic | Detail
Architecture (delivered separately)
Frontend | HTML + external CSS + vanilla JavaScript only. Standalone prototype; data in browser localStorage. Presented on its own - no backend calls.
Backend | Vanilla Java + JDBC + PostgreSQL. TERMINAL / console application. Presented on its own - NOT connected to the frontend.
Integration | OUT OF SCOPE: no REST/API layer; DB used only by the Java console app; frontend & backend demoed separately.
In scope
Roles | Institute Admin, Doctor, Receptionist, Patient (RBAC per role).
Security | SHA-256 salted hashing for passwords & security answers; 3-question recovery with lockout; consent-based document access.
Data model | Users, clinics (clinic codes), staff, patients, appointments & requests, availability, documents, consents/grants, audit log.
Delivery order | Frontend built first (done); backend terminal app + Postgres built later.
Out of scope (explicitly)
Clinical clutter | No ICD-10 billing codes, medical licensing numbers, raw vitals tables, or medication dispensing.
Platform | No mobile-native app; desktop-first web (1280-1440px). No live frontend-backend-DB connection.
Infra | No cloud deployment, CI/CD, or real email/SMS delivery in this scope.
Estimation legend
Priority | MoSCoW - Must / Should / Could.
Points | Fibonacci story points (relative effort).
Subtask Est (h) | Rough hours per subtask for task-level planning.
Status | Frontend = Done (prototype built). Backend = To Do (later phase).

## Backend DB Schema
Table | Key Columns | Notes
users | id PK, full_name, email UNIQUE, password_hash, salt, role, clinic_id FK, status, created_at | All roles incl. admin; role drives RBAC
security_questions | id PK, user_id FK, question, answer_hash | 3 rows per user; answers hashed
clinics | id PK, name, specialty, address, clinic_code UNIQUE, status, created_at | clinic_code used at staff signup
patients | id PK, user_id FK, mrn UNIQUE, dob, blood_group, phone, allergies, emergency_contact | Patient profile / digital pass data
availability | id PK, doctor_id FK, weekday, shift_start, shift_end, break_start, break_end | Doctor weekly availability
appointment_requests | id PK, patient_id FK, doctor_id FK, preferred_date, reason, status, created_at | status: pending/scheduled/declined
appointments | id PK, request_id FK, patient_id FK, doctor_id FK, clinic_id FK, date, time, visit_type, status | Created when receptionist assigns a slot
consultations | id PK, appointment_id FK, doctor_id FK, patient_id FK, note, created_at | Consultation history notes
documents | id PK, patient_id FK, file_name, mime_type, size_bytes, uploaded_at | Metadata only in backend (no blob wiring)
document_requests | id PK, doctor_id FK, patient_id FK, message, status, created_at | Privacy-preserving doc request
consents | id PK, patient_id FK, doctor_id FK, document_id FK, granted_at, expires_at, revoked_at | Granular, time-boxed access grants
audit_log | id PK, actor_user_id, action, entity, entity_id, detail, created_at | Append-only; consent grant/revoke etc.